## Sheet1
Task | Description | Estimated Time | Downtime Required | Prioritization | Tentative Schedule
Server Sizing | Add memory and adjust MAXDOP settings. | 30 minutes | Yes, restart required | 1 | 2025-01-27
Instant File Initialization (IFI) | Enable IFI to reduce overhead and downtime for file extensions. | 30 minutes | Yes, restart required | 2 | 2025-01-27
TempDB Optimization | Move TempDB to a dedicated drive. | 1 hour | Yes | 3 | 2025-01-27
Disk Configuration | Migrate data, log, and TempDB files to separate drives with 64K cluster size. | 2-8 hours | Yes, full outage | 4 | 2025-01-28
Query Store Configuration | Enable Query Store for query plan monitoring and optimization. | 3-8 hours | No | 5 | 2025-01-29
Maintenance Plans | Set up agent jobs for index reorganization, rebuilds, and statistics updates. | 5-10 hours | No | 6 | 2025-01-30
DBCC CHECKDB | Schedule and perform weekly integrity checks. | 5-6 hours total | No | 7 | 2025-01-31
VLF Count Reduction | Resize transaction logs to optimize virtual log file count. | 2-4 hours | Yes | 8 | 2025-02-06
Backup Strategy | Implement a robust backup schedule (daily FULL, hourly transaction logs). | 3-8 hours + 3 hours audit | No | 9 | 2025-02-07
Performance Tuning | Analyze unused/missing indexes, optimize queries, and address parameterization issues. | 10-30 hours | No |  | 2/3/2025-2/5/2025
Notes:
All changes/downtime will be scheduled between 10am and 8pm MT
Downtime will be avoided Monday-Wednesday after pay period close
Summary By Day |  |  |  |  | Summary By Week
Day | Week | High Hours | Low Hours |  | Week | High Hours | Low Hours
2025-01-27 | 5 | 2 | 2 |  | 5 | 34 | 17
2025-01-28 | 5 | 8 | 2 |  | 6 | 15 | 8
2025-01-29 | 5 | 8 | 3
2025-01-30 | 5 | 10 | 5
2025-01-31 | 5 | 6 | 5
2025-02-06 | 6 | 4 | 2
2025-02-07 | 6 | 11 | 6